## Summary
Item | Value | Status
Project | Clinic Building Extension
Currency | PKR
Start date | 2026-01-05
End date | 2026-06-26
Status date | 2026-04-03
Generated | 2026-10-29 23:15
Overall health | Action needed
Primary EAC method | typical, BAC ÷ CPI
Budget at completion (BAC) | 1040000
Planned value (PV) | 522926.412
Earned value (EV) | 496000
Actual cost (AC) | 570000
Cost variance (CV) | -74000 | Action needed
Schedule variance (SV) | -26926.412 | Watch
CV% | -14.92% | Action needed
SV% | -5.149% | Watch
Cost performance index (CPI) | 0.87018 | Action needed
Schedule performance index (SPI) | 0.94851 | Watch
Estimate at completion (EAC, typical, BAC ÷ CPI) | 1195161.2903 | Action needed
Estimate to complete (ETC) | 625161.2903
Variance at completion (VAC) | -155161.2903 | Action needed
To-complete performance index (TCPI) | 1.1574 | Action needed
% complete | 47.69%
% spent | 54.81%

## Tasks
Task ID | Task Name | Category | Budget (estimated cost) (PKR) | Planned Start | Planned Finish | % Complete | Actual Cost (PKR) | Variance (PKR) | % Variance | PV (PKR) | EV (PKR) | CV (PKR) | SV (PKR) | CPI | SPI | Unusual expenses
1.1 | Requirements | Labour | 50000 | 2026-01-05 | 2026-01-20 | 100% | 48000 | 2000 | 4% | 50000 | 50000 | 2000 | 0 | 1.0417 | 1
1.2 | Design | Labour | 80000 | 2026-01-21 | 2026-02-15 | 100% | 82000 | -2000 | -2.5% | 80000 | 80000 | -2000 | 0 | 0.97561 | 1
1.3 | Permits | Other | 20000 | 2026-01-21 | 2026-02-05 | 100% | 19000 | 1000 | 5% | 20000 | 20000 | 1000 | 0 | 1.0526 | 1
2.1 | Site preparation | Equipment | 60000 | 2026-02-09 | 2026-02-28 | 100% | 66000 | -6000 | -10% | 60000 | 60000 | -6000 | 0 | 0.90909 | 1
2.2 | Foundations | Subcontract | 150000 | 2026-02-23 | 2026-03-20 | 100% | 172000 | -22000 | -14.67% | 150000 | 150000 | -22000 | 0 | 0.87209 | 1
2.3 | Structural steel | Material | 200000 | 2026-03-09 | 2026-04-17 | 55% | 138000 | 62000 | 31% | 128205.1282 | 110000 | -28000 | -18205.1282 | 0.7971 | 0.858
2.4 | Masonry | Labour | 90000 | 2026-03-23 | 2026-04-24 | 25% | 32000 | 58000 | 64.44% | 30937.5 | 22500 | -9500 | -8437.5 | 0.70312 | 0.72727
3.1 | Electrical rough-in | Subcontract | 70000 | 2026-04-01 | 2026-05-08 | 5% | 9000 | 61000 | 87.14% | 3783.7838 | 3500 | -5500 | -283.7838 | 0.38889 | 0.925 | AN-01
3.2 | Plumbing rough-in | Subcontract | 65000 | 2026-04-06 | 2026-05-08 | 0% | 4000 | 61000 | 93.85% | 0 | 0 | -4000 | 0 | 0 | N/A | AN-02
3.3 | Roofing | Material | 110000 | 2026-04-20 | 2026-05-22 | 0% | 0 | 110000 | 100% | 0 | 0 | 0 | 0 | N/A | N/A
4.1 | Interior finishes | Labour | 120000 | 2026-05-11 | 2026-06-19 | 0% | 0 | 120000 | 100% | 0 | 0 | 0 | 0 | N/A | N/A
4.2 | Handover and commissioning | Other | 25000 | 2026-06-19 | 2026-06-26 | 0% | 0 | 25000 | 100% | 0 | 0 | 0 | 0 | N/A | N/A

## Snapshots
Date | PV (PKR) | EV (PKR) | AC (PKR) | CV (PKR) | SV (PKR) | CPI | SPI
2026-01-23 | 59066.67 | 60248 | 57931 | 2317 | 1181.33 | 1.04 | 1.02
2026-02-06 | 121200 | 122412 | 120012 | 2400 | 1212 | 1.02 | 1.01
2026-02-20 | 184736.84 | 182889 | 184736 | -1847 | -1847.84 | 0.99 | 0.99
2026-03-06 | 276000 | 267720 | 281811 | -14091 | -8280 | 0.95 | 0.97
2026-03-20 | 416410.26 | 399754 | 439290 | -39536 | -16656.26 | 0.91 | 0.96
2026-04-03 | 522926.41 | 496000 | 570000 | -74000 | -26926.41 | 0.87018 | 0.94851

## Insights
Rule | Status | Message | What to do
IN-03 | Action needed | Significant cost overrun: each 1 unit spent earns only 0.87 of value (CPI 0.87). | Hold a cost review now: find the overrunning tasks, cut non-essential spend and agree corrective actions.
IN-09 | Action needed | Recovering to budget is unrealistic: the remaining work would need a TCPI of 1.16 (more than 1.10). Consider re-baselining to the EAC of PKR 1,195,161.29. | Finishing on budget is unlikely. Agree a new budget (re-baseline) using the EAC with stakeholders.
IN-10 | Action needed | Forecast overrun of PKR 155,161.29 (14.92%) at completion. | Report the forecast overrun to stakeholders and plan how it will be funded or reduced.
IN-05 | Watch | Slightly behind schedule: only 94.85% of the planned work is done (SPI 0.95). | Look at the tasks that are behind plan and whether extra resources or re-sequencing can help.
IN-11 | Watch | Cost efficiency is trending down: CPI fell for 3 consecutive snapshots (0.99 → 0.95 → 0.91 → 0.87). | Find out what changed in recent periods before the trend becomes a large overrun.
IN-12 | For information | Main contributors to overrun: 2.3 Structural steel (CV -PKR 28,000.00), 2.2 Foundations (CV -PKR 22,000.00), 2.4 Masonry (CV -PKR 9,500.00). | Start with these tasks: they explain most of the overrun.

## Anomalies
Rule | Severity | Task ID | Snapshot date | Reason
AN-01 | High | 3.1 |  | Task 3.1 has a cost variance of -157.14%, far from the other tasks (average -30.37%, z-score -2.53).
AN-02 | Medium | 3.2 |  | Task 3.2 has spent PKR 4,000.00 but is 0% complete.

## AI Summary
Field | Text
Source | Generated offline (rule-based)
Reason | AI service not configured
Generated | 2026-10-29 23:14
Up to date | Yes
Executive summary | Clinic Building Extension is 47.69% complete and has spent 54.81% of its PKR 1,040,000.00 budget as of 2026-04-03. The project is significantly over budget (CPI 0.87). Work is slightly behind schedule (SPI 0.95). The forecast at completion is PKR 1,195,161.29, an overrun of PKR 155,161.29 (14.92%). 2 unusual expenses were flagged (1 high severity).
Key risk 1 | Significant cost overrun: each 1 unit spent earns only 0.87 of value (CPI 0.87).
Key risk 2 | Recovering to budget is unrealistic: the remaining work would need a TCPI of 1.16 (more than 1.10). Consider re-baselining to the EAC of PKR 1,195,161.29.
Key risk 3 | Forecast overrun of PKR 155,161.29 (14.92%) at completion.
Key risk 4 | Slightly behind schedule: only 94.85% of the planned work is done (SPI 0.95).
Recommendation 1 | Hold a cost review now: find the overrunning tasks, cut non-essential spend and agree corrective actions.
Recommendation 2 | Finishing on budget is unlikely. Agree a new budget (re-baseline) using the EAC with stakeholders.
Recommendation 3 | Report the forecast overrun to stakeholders and plan how it will be funded or reduced.